## Roadmap Gantt
ID | Area | Task | Class | Status % | Weight (days) | Days left | Priority | Phase | Notes
1 | Core | Ranking Transparency Debugger | A | 100 | 2-3 | 0 | Done | Technical | Closed
2 | Core | Dataset cleanup critico | A | 95 | 3-5 | 0.5-1 | High | Technical | Almost closed
3 | Core | Output data quality | A | 95 | 1-2 | 0.25-0.5 | High | Technical | Producer/name cleaner
4 | Core | Match refinement food | B | 90 | 3-4 | 0.5-1 | High | Technical | Specific food queries good
5 | Core | Match refinement occasion/style/prestige/elegance | B | 88 | 5-7 | 1-2 | High | Technical | Very advanced
6 | Core | Performance + cache | B | 75 | 2-3 | 0.5-1 | Medium | Technical | Realigned
7 | Governance | Tuning score/fallback/bonus with tracking | C | 60 | 2-4 | 1-2 | High | Technical | Governed by A/B/C/D
8 | Governance | Golden tests / query baseline | C | 90 | 1-2 | 0.25-0.5 | High | Technical | GT defined
9 | Docs | Release notes + structured handoff | D | 90 | 1-2 | 0.25-0.5 | High | Closure | Near complete
10 | Docs | Final freeze + regression check | D | 70 | 1 | 0.25-0.5 | High | Closure | Pending final pass
11 | Strategy | Source strategy wines | E | 10 | 3-6 | 3-5 | Critical | Strategic | Fundamental open decision
12 | Strategy | Catalog model / mapping / data quality | E | 5 | 2-4 | 2-4 | Critical | Strategic | Depends on source decision
13 | LLM | Define LLM role and boundaries | F | 0 | 1-2 | 1-2 | High | Product | After source strategy direction
14 | LLM | Implement LLM v1 useful behavior | F | 0 | 3-5 | 3-5 | High | Product | Follow-up / refinement / reasoning
15 | Launch | Positioning and product message | G | 10 | 2-3 | 2-3 | High | Go-to-market | Still open
16 | Launch | Launch strategy / channels / pricing / alpha-beta | G | 0 | 3-5 | 3-5 | High | Go-to-market | Still open

## Summary
Metric | Value
Technical block progress | ~88%
Complete project progress | ~55–60%
Days left to close current technical block | 2–4 working days
Most likely remaining time (technical block) | 3 working days
LLM v1 after current block | +4–7 working days
Source strategy + launch residual | +7–14 working days
Complete project estimate | 3–6 weeks
Most likely complete project estimate | ~4 weeks
Critical open decision | Wine source strategy / catalog sourcing